## Gantt Chart
GANTT CHART

PROJECT TITLE		GP APPLICATION
PRODUCT OWNER		Vina Panduwinata					DATE					15/11/21

Number	Activity Title	Assigned To	Start Date	End Date	Duration	% of Completed Activities	Sprint 1					Sprint 2					Sprint 3					Sprint 3					Sprint 4					Sprint 5					Sprint 6					Sprint 7					Sprint 8					Sprint 8
					Week 1					Week 2					Week 3					Week 4					Week 5					Week 6					Week 7					Week 8					Week 9					Week 10					Week 11					Week 12					Week 11					Week 12					Week 11					Week 12					Week 11					Week 12					Week 13					Week 14
					M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F	M	T	W	T	F
1	Kick off meeting
1.1	Project specification	Product owner	13/12/21	17/12/21	5	100 %
1.1.1	Project specification revision	Product owner	16/12/21	20/12/21	3	100 %
1.2	Collect information of client's need	Product owner	17/12/21	20/12/21	2	100 %
1.3	Projection of the project budget	Product owner	20/12/21	22/12/21	3	100 %
1.4	Guidelines	Product owner	23/12/21	24/12/21	2	100 %
2	Business process proposal
2.1	Define the scope and objectives	Product owner	05/01/22	07/01/22	3	100 %
2.2	Budget	Product owner	10/01/22	12/01/22	3	100 %
2.3	Communication plan	Product owner	13/01/22	17/01/22	5	100 %
2.4	Risk management	Product owner	17/01/22	19/01/22	3	100 %
2.5	Project agreement	Product owner	20/01/22	21/01/22	2	100 %
3	Start of the project
3.1	Forming the team	Scrum master	10/01/22	21/01/22	12	100 %
3.2	PROJECT RETROSPECTIVE	Scrum master	24/01/22	24/01/22	1	100 %
3.2.1	Provide list of work	Scrum master				102 %
3.2.2	Determine the most valuable product	Scrum master				103 %
3.2.3	Provide the list of technology (cloud, 3rd party API)	Scrum master				104 %
3.2.4	Setting up versioning control and invite the team member	Scrum master				105 %
3.3	SPRINT 1
3.3.1	Mockup design for UI	UI/UX designer	25/01/22	14/03/22	35	30 %
3.3.2	Mockup revision	UI/UX designer	26/01/22	15/03/22	35	20 %
3.3.3	Front End Development for reservation	Front end dev	25/01/22	10/02/22	14	10 %
3.3.4	Setting up the db	Back end dev	25/01/22	10/02/22	14	10 %
3.3.5	Documentation for list of queries	Db developer	26/01/22	10/02/22	13	10 %
3.3.6	Setting up the link for reservation API	Back end dev	28/01/22	10/02/22	11	0 %
3.3.7	Product change (if any)	Scrum master	26/01/22	28/01/22	3	0 %
3.3.8	Sprint review	Scrum master	11/02/22	11/02/22	1	0 %
3.4	PROJECT RETROSPECTIVE	Scrum master	14/02/22	14/02/22	1	0 %
3.5	SPRINT 2
3.5.1	Revision for bugs	Back end/front end dev	14/02/22	18/02/22	5	0 %
3.5.2	Front End Development for visit	Front end dev	14/02/22	24/02/22	9	0 %
3.5.3	Documentation for list of queries	Db developer	14/02/22	24/02/22	9	0 %
3.5.4	Setting up the link for visit API	Back end dev	14/02/22	24/02/22	9	0 %
3.5.5	Product change (if any)	Scrum master	14/02/22	16/02/22	3	0 %
3.5.6	Sprint review	Scrum master	25/02/22	25/02/22	1	0 %
3.6	PROJECT RETROSPECTIVE	Scrum master	28/02/22	28/02/22	1	0 %
3.7	SPRINT 3
3.7.1	Revision for bugs	Back end/front end dev	28/02/22	04/03/22	5	0 %
3.7.2	Front End Development for online meeting	Front end dev	28/02/22	10/03/22	9	0 %
3.7.3	Documentation for list of queries	Db developer	28/02/22	10/03/22	9	0 %
3.7.4	Setting up the link for online meeting API	Back end dev	28/02/22	10/03/22	9	0 %
3.7.5	Product change (if any)	Scrum master	28/02/22	02/03/22	3	0 %
3.7.6	Sprint review	Scrum master	11/03/22	11/03/22	1	0 %
3.8	PROJECT RETROSPECTIVE	Scrum master	14/03/22	14/03/22	1	0 %
3.9	SPRINT 4
3.9.1	Revision for bugs	Back end/front end dev	14/03/22	18/03/22	5	0 %
3.9.2	Front End Development for offline meeting	Front end dev	14/03/22	24/03/22	9	0 %
3.9.3	Documentation for list of queries	Db developer	14/03/22	24/03/22	9	0 %
3.9.4	Setting up the link for offline meeting API	Back end dev	14/03/22	24/03/22	9	0 %
3.9.5	QA testing	QA tester	18/03/22	24/03/22	7	0 %
3.9.6	Product change (if any)	Scrum master	14/03/22	16/03/22	3	0 %
3.9.10	Sprint review	Scrum master	25/03/22	25/03/22	1	0 %
3.10	PROJECT RETROSPECTIVE	Scrum master	28/03/22	28/03/22	1	0 %
3.11	SPRINT 5
3.11.1	Revision for bugs	Back end/front end dev	28/03/22	01/04/22	5	0 %
3.11.2	Front End Development for diagnosis	Front end dev	28/03/22	07/04/22	9	0 %
3.11.3	Documentation for list of queries	Db developer	28/03/22	07/04/22	9	0 %
3.11.4	Setting up the link for diagnosis API	Back end dev	28/03/22	07/04/22	9	0 %
3.11.5	QA testing	QA tester	01/04/22	07/04/22	7	0 %
3.11.6	Product change (if any)	Scrum master	28/03/22	30/03/22	3	0 %
3.11.7	Sprint review	Scrum master	08/04/22	08/04/22	1	0 %
3.12	PROJECT RETROSPECTIVE	Scrum master	11/04/22	11/04/22	1	0 %
3.13	SPRINT 6
3.13.1	Revision for bugs	Back end/front end dev	11/04/22	15/04/22	5	0 %
3.13.2	Front End Development for medical prescription : dosage	Front end dev	11/04/22	21/04/22	9	0 %
3.13.3	Documentation for list of queries	Db developer	11/04/22	21/04/22	9	0 %
3.13.4	Setting up the link for dosage	Back end dev	11/04/22	21/04/22	9	0 %
3.13.5	QA testing	QA tester	15/04/22	21/04/22	7	0 %
3.13.6	Product change (if any)	Scrum master	11/04/22	13/04/22	3	0 %
3.13.7	Sprint review	Scrum master	22/04/22	22/04/22	1	0 %
3.14	PROJECT RETROSPECTIVE	Scrum master	25/04/22	25/04/22	1	0 %
3.15	SPRINT 7					0 %
3.15.1	Revision for bugs	Back end/front end dev	25/04/22	29/04/22	5	0 %
3.15.2	Front End Development for medical prescr : procedure	Front end dev	25/04/22	05/05/22	9	0 %
3.15.3	Documentation for list of queries	Db developer	25/04/22	05/05/22	9	0 %
3.15.4	Setting up the link for procedure	Back end dev	25/04/22	05/05/22	9	0 %
3.15.5	QA testing	QA tester	29/04/22	05/05/22	7	0 %
3.15.6	Product change (if any)	Scrum master	25/04/22	27/04/22	3	0 %
3.15.7	Sprint review	Scrum master	06/05/22	06/05/22	1	0 %
3.16	PROJECT RETROSPECTIVE	Scrum master	09/05/22	09/05/22	1	0 %
3.17	SPRINT 8					0 %
3.17.1	Revision for bugs	Back end/front end dev	09/05/22	13/05/22	5	0 %
3.17.2	Front End Development for control	Front end dev	09/05/22	19/05/22	9	0 %
3.17.3	Documentation for list of queries	Db developer	09/05/22	19/05/22	9	0 %
3.17.4	Setting up the link for control	Back end dev	09/05/22	19/05/22	9	0 %
3.17.5	QA testing for control	QA tester	13/05/22	19/05/22	7	0 %
3.17.6	Product change (if any)	Scrum master	09/05/22	11/05/22	3	0 %
3.17.7	Sprint review	Scrum master	20/05/22	20/05/22	1	0 %
3.18	QA testing for all of the function	QA tester	19/05/22	03/06/22	12	0 %
3.19	Bugs review	Product owner	23/05/22	03/06/22	11	0 %
3.20	Bugs fixing	Developer	23/05/22	03/06/22	11	0 %
3.21	Creating User manual	Product owner	23/05/22	03/06/22	11	0 %
3.22	UAT	Scrum master	01/06/22	03/06/22	3	0 %
3.23	Bugs review	Product owner	01/06/22	03/06/22	3	0 %
3.24	Bugs fixing	Developer	01/06/22	03/06/22	3	0 %
3.25	Deployment to production cloud	Scrum master	06/06/22	10/06/22	5	0 %
3.26	Testing on production	QA tester	06/06/22	10/06/22	5	0 %
3.27	Fixing error on production	Scrum master, assign to developer	06/06/22	10/06/22	5	0 %
4	Going Live
4.1	User training	Scrum master	13/06/22	17/06/22	5	0 %
4.2	Live to production	Product owner	20/06/22	20/06/22	1	0 %
5	After live support
5.1	Monitoring performance	Scrum master	20/06/22	19/08/22	42	0 %
5.2	Receiving issue ticket	Scrum master	20/06/22	19/08/22	42	0 %
5.3	Project handover documentation	Product owner	22/08/22	22/08/22	1	0 %
5.4	Finish the project (signature)	Product owner	22/08/22	22/08/22	1	0 %