## Slide 1
PROJECT STRUCTURE
Vina Panduwinata
Mat. 492243

## Slide 2
Structure
PRODUCT
PRODUCT ACTIVITIES
ORGANIZATION
PROJECT STRUCTURE

## Slide 3
PRODUCTS Breakdown 1.1. List of candidate deliverables(I)
Software
GP App
Reservation
Visitation
Diagnosis
Medical Prescription
Suggestion

## Slide 4
PRODUCTS Breakdown 1.1. List of candidate deliverables (II)
Technologies
Architecture
Elements
Internet
Database Management System
Peer to Peer cloud connection
Firewall
Cloud
Laptop/PC

## Slide 5
PRODUCTS Breakdown 1.1. List of candidate deliverables (III)
Organizations
Transformation
Business Process
GP Training
GP Service
Medical Procedure
Manual
New visit/booking rules
Desktop/web application
Business Outcome
Business Action
Marketing
3rd Party Connection

## Slide 6
PRODUCTS Breakdown 1.2.Agreggation/Division(I)
Software
GP App
Reservation
Visitation
Diagnosis
Medical Prescription
Suggestion
1
1
2
2
2

## Slide 7
PRODUCTS Breakdown 1.2. Agreggation/Division (II)
Technologies
Architecture
Elements
Internet
Database Management System
Peer to Peer cloud connection
Firewall
Cloud
Laptop/PC
1
1
1
1
1
2

## Slide 8
PRODUCTS Breakdown 1.2. Agreggation /Division (III)
Organizations
Transformation
Business Process
GP Training
GP Service
Medical Procedure
Manual
New visit/booking rules
GP Desktop/web app
Business Outcome
Business Action
Marketing
3rd Party Connection
1
1
1
2
3
2
3
3

## Slide 9
ction
Organization
03
GP Training
GP Services
New Visit/Booking Rules
Medical Procedure
GP Desktop/Web App
Technology
02
Internet
Database Management System
Peer to peer Cloud Connection
Firewall
Laptop/PC
Cloud
Software GP Application
01
Reservation
Visitation
Diagnosis
Medical Prescription
Suggestion
PRODUCTS Breakdown
1.3. Product List
3. Manual
Marketing
3rd Party Connection

## Slide 10
Work packages
WP # : |  | Start date or starting event |  |  | 13/12/2021 | 
WP title : | GP application |  |  |  |  | 
Participant # | 1 | 2 | 3 | 4 | 5 | 
Participant | GP | Specialist | LAB | Region | Patient | 
Effort |  |  |  |  |  | 
Work Package | Participant # : | Description |  |  |  | 
1. Kick off meeting | GP, Lab | Include GP and LAB as stakeholder in the application |  |  |  | 
2. Business proposal | Region | Include region when creating business proposal and propose budget |  |  |  | 
3. Data observation | GP, specialist, LAB | Do survey and observation with GP, specialist and lab to get acquinted with the real problem in their field |  |  |  | 
4. MVP meeting | GP | Choose the most value representative of the product |  |  |  | 
5. UAT | GP, specialist, LAB, patient, region | Each of the representative can provide better feedback for the system |  |  |  | 
6. User training | GP, specialist, LAB, patient, region | Sharing manual of the system, by doing education to school, pharmacy or hospital and get quick feedback from the user |  |  |  | 
7. Live support | GP, LAB, patient | Provide helper for direct user of the system |  |  |  | 

## Slide 11
Project milestone (I)
Mile
stone
Kick off meeting
Deadline (month) | Actions | Decision to be made
 | Accomplish | No required action
 | Accomplish | No required action
 | Accomplish | No required action
 | Accomplish | No required action
12 | 01 | 02 | 03 | 04 | 05 | 06 | 07
Business Proposal
Team
forming
MVP meeting
Start-end
Complete

## Slide 12
Project milestone (II)
Mile
stone
Mockup design
Deadline (month) | Actions | Decision to be made
 | Sharing the design in every sprint and with project management/version control platform like Jira, Github or Trello | Change requirements still accepted during the 70% of project timeline
 | Start with the most valuable product of this project, develop the prototype and do the test and deployment in development environment | Accelerate the phase of this menu to be delivered on time, revision of the bug can be done in parallel
 | Review the UI from the UI/UX designer for this menu | To be discussed at the sprint review
 | Review the UI from the UI/UX designer for this menu | To be discussed at the sprint review
12 | 01 | 02 | 03 | 04 | 05 | 06 | 07
Reservation menu
Visit
menu
Diagnosis menu
Start-end
Complete
In progress

## Slide 13
Project milestone (II)
Mile
stone
Prescription menu
Deadline (month) | Actions | Decision to be made
 | Review the UI from the UI/UX designer for this menu | To be discussed at the sprint review
 | For each deployment to the development cloud need to be tested by QA tester | Inform to the bug or fault to the scrum team in sprint review
 | Invite some stakeholder representatives to join UAT | If there is minor bug or changes for the UI, and can be accommodated in timeline, then approve
 | Provide the list of actions to migrate from development cloud to production cloud, or mirroring the environment | Consider the difficulties of migration
12 | 01 | 02 | 03 | 04 | 05 | 06 | 07
QA testing
UAT
Deployment
Start-end
Complete
In progress

## Slide 14
Project milestone (II)
Mile
stone
User training
Deadline (month) | Actions | Decision to be made
 | Do socialization in the school, hospital or pharmacies, advertisement via web, television or billboard | Consider the budget for the advertisement and training
 | Stand by for unexpected bug or risk | Consider user response of the system, control the use of production budget
 | Monitoring performance of the system, provide helpdesk support | By using system monitoring, we can decide if the infrastructure of the cloud suitable or we can make cost optimization
12 | 01 | 02 | 03 | 04 | 05 | 06 | 07
Going live
Live support
Start-end
Complete
In progress

## Slide 15
Gantt chart refer to the attachment